## AHUFLYER
Air Handling Unit Systems Test Reports

## ahu1
INTERNAL USE ONLY - DOES NOT PRINT
GENERAL FIELD CALC. AREA
AIR HANDLING UNIT TEST REPORT
PROJECT | [12 empty] | SYSTEM |  | ahu1
AREA SERVED | [12 empty] | LOCATION
UNIT DATA | [12 empty] | FILTER DATA | [8 empty] | MOTOR ACTUAL BHP CALCS.
MFG. | [12 empty] | FILTER SECTION | [9 empty] | AMPS. | VOLTS |  |  |  |  | AMP IMBALANCE TEST1 |  | VOLT IMBALANCE TEST2
TYPE | [12 empty] | QUANTITY | [8 empty] | TEST 1 |  |  | MOTOR EFF.
MODEL NO. | [12 empty] | SIZE (in.) | [8 empty] | TEST 2
SERVICE |  |  |  | Conditioned Air | [8 empty] | TYPE | [8 empty] | TEST 3 |  |  | POWER FACTOR
SERIAL NO. | [12 empty] | S.P. ACROSS |  |  |  | "w.c. |  |  | "w.c. |  | AVG. | [6 empty] | 1. Amp imbalance may indicate problems with the motor or power supply.
[13 empty] | CONDITION | [11 empty] | MOTOR PHASE |  |  |  | 2. Volt imbalance may cause motors to overheat. Many solid-state motor controllers and inverters are sensitive to imbalanced voltage.
SUPPLY FAN DATA
|  | CFM |  | TSP |  | ESP |  | RPM |  | BHP |  | ROTATION | [9 empty] | POWER TRANSMISSION (PT) CALCS. | [7 empty] | DETERMINING FAN ROTATION
DESIGN |  | 100 | [19 empty] | MTR TO FAN SHEAVE RATIO
ACTUAL | [21 empty] | CALC. BELT LENGTH |  |  |  |  | "
FAN MOTOR RPM PER PT
AIRFLOW DATA | [11 empty] | POWER TRANSMISSION DATA |  |  |  |  | X |  |  |  |  | MIN. FAN MTR RPM PER PT1
|  |  |  | RETURN |  |  | OUTSIDE |  |  |  |  | TRANSMISSION TYPE | [9 empty] | 1. If fan motor RPM falls below this min. number (cell red) check for belt slippage or belt riding on motor shaft. Based on 0.5" reduction on motor and fan sheave.
DESIGN (CFM) | [11 empty] | MOTOR SHEAVE MFG.
ACTUAL (CFM) | [11 empty] | MOTOR SHEAVE |  |  |  |  | "I.D. |  |  | "O.D.
DAMPER POS. | [5 empty] | Open |  |  | Open |  |  | FAN SHEAVE MFG.
[12 empty] | FAN SHEAVE |  |  |  |  | "I.D. |  |  | "O.D.
MOTOR DATA |  |  | X | [8 empty] | BELT MFG.
MFG. | [11 empty] | NO. BELTS & SIZE | [5 empty] | @
FRAME | [11 empty] | CENTER DISTANCE | [6 empty] | "C.C.
H.P. | [21 empty] | DUCT DP SETPOINT CALC. (+20% Tol.)
SERVICE FACTOR | [15 empty] | DUCT STATIC PRESSURE
[5 empty] | DESIGN |  |  | ACTUAL | [7 empty] | SETPOINT |  |  |  | "w.c.
RPM | [15 empty] | ACT. MEASUREMENT |  |  |  | "w.c.
FULL LOAD AMPS. | [7 empty] | ---
CRT. NAME AMPS. |  |  |  |  | ---
OP. AMPS. |  |  |  |  | --- | [8 empty] | SUPPLY FAN SPEED FINAL SETTING | [7 empty] | STATIC PRESSURE PROFILE SELECTIONS |  |  |  | BASIC TESTING WORKFLOW (Indicate Complete with x)
VOLTS | [26 empty] | 1
[22 empty] | A - B |  |  |  |  | 2 | Verify duct layout (areas served) vs drawings and neck sizes.
STATIC PRESSURE PROFILE "w.c. | [21 empty] | B - C |  |  |  |  | 3 | Check nameplate against submittal.
COMPONENT | [21 empty] | C - D |  |  |  |  | 4 | Open dampers and check that automatic dampers open when the system is energized.
[22 empty] | D - E |  |  |  |  | 5 | Check pulley alignment and tightness.
[22 empty] | E - F |  |  |  |  | 6 | Put the unit into full cooling.
[22 empty] | F - G |  |  |  |  | 7 | Check rotation.
PRESSURE | [21 empty] | G - H |  |  |  |  | 8 | Measure the inlets / outlets on the system.
[22 empty] | H - I |  |  |  |  | 9 | Proportion the inlets / outlets to the available airflow.
[22 empty] | I - J |  |  |  |  | 10 | Adjust rpm as needed to achieve design airflow based on rpm vs cfm equation.
| REMARKS | [20 empty] | J - K |  |  |  |  | 11 | Adjust outside and return air to design.
[27 empty] | 12 | Measure rpm, amperage and voltage.
[27 empty] | 13 | Measure inlets / outlets on the system.
[27 empty] | 14 | Record unit pressure profile (before filter, after filter, suction and discharge pressures etc.)
[27 empty] | 15 | Measure the entering and leaving chilled water pressure and set to design if applicable.
[27 empty] | 16 | Measure the entering and leaving dry and wet bulb temperatures across the cooling coil.
[27 empty] | 17 | Put the unit into full heating if applicable.
[27 empty] | 18 | Measure the total airflow and record differences to design.
[27 empty] | 19 | Measure electric heating components or heating hot water pressures and set to design.
[27 empty] | 20 | Measure entering and leaving air temperature (dry bulb only).
[26 empty] | Note - Measure total supply, return and outside airflows by traverse when possible. |  | Make sure all information on the data sheet is filled out.
TEST DATE | [10 empty] | READINGS BY
LOOKING
CCW

## ahu1 - OUTLETSUM-1
INTERNAL USE ONLY - DOES NOT PRINT
OUTLET TEST REPORT
PROJECT | [6 empty] | SYSTEM |  | ahu1
PROJECT TOLERANCES
[16 empty] | ABOVE DESIGN | GENERAL FIELD CALC. AREA
[14 empty] | FOR PROPORTIONS, CORRECTION FACTORS, ETC. |  | BELOW DESIGN
AREA SERVED LOCATION |  | OUTLETS |  |  |  | DESIGN CFM | PRELIMINARY CFM |  |  |  | FINAL CFM | REMARKS
|  | NO. | TYPE |  | SIZE (IN.) |  | TEST1 | TEST 2 |  | TEST 3 |  |  |  |  | FINAL CFM TOLERANCE CHECK
1
2
3
4
5
TOTAL
REMARKS
TEST DATE | [5 empty] | READINGS BY

## ahu1 - INLETSUM-1
INTERNAL USE ONLY - DOES NOT PRINT
DUCTED RETURN TEST REPORT
PROJECT | [6 empty] | SYSTEM |  | ahu1
PROJECT TOLERANCES
[16 empty] | ABOVE DESIGN | GENERAL FIELD CALC. AREA
[14 empty] | FOR PROPORTIONS, CORRECTION FACTORS, ETC. |  | BELOW DESIGN
AREA SERVED LOCATION |  | INLETS |  |  |  | DESIGN CFM | PRELIMINARY CFM |  |  |  | FINAL CFM | REMARKS
|  | NO. | TYPE |  | SIZE (IN.) |  | TEST1 | TEST 2 |  | TEST 3 |  |  |  |  | FINAL CFM TOLERANCE CHECK
1
2
3
TOTAL
REMARKS
TEST DATE | [5 empty] | READINGS BY